## Burndown Chart
Sprint 2 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | General problem fixing | 2 |  | 1 | 1
2 | Brain storm on how to implement | 4 | 1 |  | 1 |  | 2
3
4
5
Completed Effort |  | 0 | 1 | 1 | 2 | 0 | 2
Remaining Effort |  | 6 | 5 | 4 | 2 | 2 | 0
Ideal Burndown |  | 6 | 5.6 | 5.2 | 4.8 | 4.4 | 4