## Folha1
Task |  | Start Date | End date | Done by | Status
Phase 1
1.1 -Project creation | 1.1.1- Repository creation | 2022-10-18 | 2022-10-19 | Martim Costa 64901, Ana Gadelha 59943 | Done
| 1.1.2-Identify code smells | 2022-10-19 | 2022-10-21 | All | Done
| 1.1.3- Identify GoF design patterns | 2022-10-20 | 2022-10-21 | All | Done
| 1.1.4-Review each others work | 2022-10-21 | 2022-10-22 | All | Done
| 1.1.5-Make report | 2022-10-21 | 2022-10-22 | All | Done
Phase 2
2.1 - New functionalities | 2.1.1- Brain storm 2 new functionalities | 2022-11-07 | 2022-11-08 | All | Done
| 2.1.2- Come up with the user stories | 2022-11-08 | 2022-11-09 | All | Done
| 2.1.3- Write the report | 2022-11-09 | 2022-11-09 | Martim Costa 64901, Pedro Arruda 60663 | Done