## Folha1
Task ID | Task Description | Initial Estimate | 2022-11-28 | 2022-11-29 | 2022-11-30
|  | Day 0 | Day 1 | Day 2 | Day 3
1 | Study the code | 1 | 1
2 | Start Implementating the new functionalities | 4 | 1 | 2 | 1
3 | Analyse metrics | 2 | 1 | 1
4 | Review metrics analyses | 2 |  | 1 | 1
5
Completed Effort |  | 0 | 3 | 4 | 2
Remaining Effort |  | 9 | 6 | 2 | 0
Ideal Burndown |  | 9 | 8.4 | 7.8 | 7.2